## Sheet1
See column descriptions in other tab
ID | User Story | Sprint Number | Story Priority | Story Status | Story Points
1 | As a user, It is important I do not tire of the game after one playthrough, so that I continue playing the game. | 2 | Low | D | 4
2 | As a user, I want the game to be accessible no matter my situation, so that whenever I want to play it I can. | 4 | Low | IP | 4
3 | As a user, I want a feeling of satisfaction upon completing the game, so that it feels that it was worthwhile to play the game. | 4 | Low | D | 2
4 | As a user, I want the default settings to generate a game that’s not too difficult or too easy, so that I do not need to mess with settings to be able to play the game. | 1 | Medium | D | 3
5 | As a user, I want to be able to customize the game to increase/decrease the difficulty in various ways, so that I can adjust the game to fit my skill level. | 4 | High | IP | 2
6 | As a user, I want a pause function, so that I can interrupt my gameplay at ease, without causing myself to instantly lose the game. | 4 | High | IP | 2
7 | As a user, I want to be able to change the color of my player character, so that I can play the game in a wide range of environments. | 5 | Medium | D | 1
8 | As a user, I want to be able to share my score with my friends, so that I can collaborate with other players to strategize for the game. | 2 | Medium | To Do | 2
9 | As a user, I want to be able to restart my current run of the game, so that if I am unsatisfied with my current run I can try again. | 1 | Medium | To Do | 1
10 | As a user, I want to unlock things as I play so that I’m incentivized to play again, so that the game never gets stale with repetitive actions. | 3 | Medium | To Do | 3
11 | As a user, I want to be able to toggle between different game modes so that there’s more variety between runs. | 5 | High | D | 3
12 | As a user, I want to be able to toggle between settings such as speed, grid size, etc., so that I can tune the game difficulty to my own needs. | 5 | Medium | To Do | 1
13 | As a user, I want to be able to know my score so that I have a metric to measure how well I performed. | 1 | High | D | 1
14 | As a user, I want the controls to be responsive so that I feel in control of the snake at all times. | 1 | High | IP | 3
15 | As a user, I want the snake to be visually distinct, so that I can easily distinguish the snake from the background. | 3 | Medium | D | 1
16 | Create the Development Environment | 1 | High | D | 2
17 | Establish User Stories | 1 | High | D | 2
18 | Project Description | 1 | High | D | 1
19 | Create Logo | 2 | Low | D | 1
20 | Create background | 2 | Low | D | 1
21 | Create default snake sprite | 2 | Low | D | 1
22 | Paper Prototype | 2 | Low | D | 2
23 | MVC Architecture Document | 2 | Low | D | 1
24 | Sprint Review | 1 | Low | D | 1
25 | Use Case Descriptions | 3 | Medium | D | 2
26 | Develop the main menu UI | 4 | High | D | 2
27 | Create the testing framweork | 3 | High | D | 2
28 | Deliverable 2 Corrections | 3 | Medium | IP | 2
29 | Continuous Integration | 3 | Medium | D | 1
30 | Video Overview | 3 | Medium | D | 1
31 | Domain Model | 3 | Low | D | 2
32 | Switch the game dev environment to JS from Pygame | 3 | High | D | 3
33 | Finish one feature | 4 | High | D | 3
34 | Finish one new feature | 4 | High | D | 3
35 | Finish another new feature | 4 | High | D | 3
36 | Finish the detailed tech design | 4 | Medium | D | 2
37 | Create another video overview | 4 | Low | D | 1
38 | Video Overview of the Project | 5 | High | To Do | 3
39 | Deliverable 3 Corrections | 5 | High | To Do | 2
40 | Deliverable 4 Corrections | 5 | High | To Do | 2
41 | Skin Tests | 5 | Medium | D | 1

## Description of Columns
ID: unique # for each story * Story: Contains the user stories (one story per row) in priority order ▪ Formatted as “As a <user role>, I need to <feature needed> because of <benefit>. o Sprint: The story’s sprint number (when it gets implemented) o Priority: H (high), M (medium), L (low) o Status: Backlog, To Do, IP (in progress), QC (quality checking), D (done) o Estimate / Story Points: Number of story points gives an indication of the difficulty of the story’s development and testing as well as possibly an estimate of the number of hours to design, implement, and test the story.
The basic idea of story points is a story with 3 points is 3x the effort as a 1 point story, 2 points is 2x the effort, etc. In general without much experience it's hard for you to estimate relative feature sizes. Just do your best. Here's more information https://www.mountaingoatsoftware.com/blog/what-are-story-points