## Sprint i
ID | User Story | Story Tasks | Sprint Number | Sprint Goal | Story Type | Story Points | Story Points Completed | Names and Contribution Percentage
15 | As a user, I want the snake to be visually distinct, so that I can easily distinguish the snake from the background. | Started to decide how to do this with our UI Mockup | 1 | Create a rough sprite | F:KA | 1 | 0 | Matthew - 0%, Makai - 0%, Tyler - 100%, George - 0%, Camron - 0% | Matthew - _%, Makai - _%, Tyler - _%, George - _%, Camron - _%
16 | Create the Development Environment | First created a frontend for the development using Vite Project, then created a venv for pygame as our backend | 1 | Create the development environment for Super-Snake | F:T | 2 | 2 | Matthew - 100%, Makai - 0%, Tyler - 0%, George - 0%, Camron - 0%
17 | Establish User Stories | Each contributor created 3 user stories. Then, each contributor quality checked 3 (or more) other user stories | 1 | Establish 15 user stories for features we want to develop over the entire sprint. | NF:KA | 2 | 2 | Matthew - 20%, Makai - 20%, Tyler - 20%, George - 20%, Camron - 20%
18 | Project Description | Updated the Project Description | 1 | Formally finish and finalize our project description | NF:KA | 1 | 1 | Matthew - 20%, Makai - 20%, Tyler - 20%, George - 20%, Camron - 20%
19 | Create Logo | Design our logo for the game | 2 | Complete a draft for the logo | F:KA | 1 | 1 | Matthew - 100%, Makai - 0%, Tyler - 0%, George - 0%, Camron - 0%
20 | Create background | Create a default background | 2 | Complete a draft for the background | F:KA | 1 | 1 | Matthew - 90%, Makai - 0%, Tyler - 10%, George - 0%, Camron - 0%
21 | Create default snake sprite | A base snake sprite to be used as the default | 2 | Complete a draft for the default sprite | F:KA | 1 | 1 | Matthew - 90%, Makai - 0%, Tyler - 0%, George - 0%, Camron - 10%
22 | Paper Prototype | Make a paper prototype for class | 2 | Complete Paper Prototype | NF:KA | 2 | 2 | Matthew - 0%, Makai - 0%, Tyler - 0%, George - 5%, Camron - 95%
23 | MVC Architecture Document | Create a document outlining our architecture | 2 | Complete Architecture Document | NF:KA | 1 | 1 | Matthew - 40%, Makai - 0%, Tyler - 0%, George - 60%, Camron - 0%
24 | Sprint Review | Review our sprint, noting successes and failures | 2 | Complete Sprint Review Document | NF:KA | 1 | 1 | Matthew - 5%, Makai - 85%, Tyler - 5%, George - 0%, Camron - 5%
25 | Use Case Descriptions | Create a document outlining our use cases, including 2 use case diagrams and descriptions for each individual use case | 2 | Complete Use Case Document | NF:KA | 2 | 2 | Matthew - 35%, Makai - 10%, Tyler - 25%, George - 20%, Camron - 10%
26 | Develop the main menu UI | Create the basic UI for the main menu. This includes the play button, and several other settings within the main menu (skin options, difficulty options, gamemodes, e.t.c.) | 2 | Framework the UI and add basic spritework | F:T | 2 | 2 | Matthew - 25%, Makai - 13%, Tyler - 35%, George - 13%, Camron - 13%
27 | Create the testing framweork | Install a working testing framework, and write a basic test. | 3 | Write atleast one working test. | F:T,B | 2 | 2 | Matthew - 100%, Makai - 0%, Tyler - 0%, George - 0%, Camron - 0%
28 | Deliverable 2 Corrections | Correct the documents (SRS, use case, e.t.c.) based on feedback from the Instructor | 3 | Complete | NF:KA | 2 |  | Matthew - _%, Makai - _%, Tyler - _%, George - _%, Camron - _%
29 | Continuous Integration | Defend from Troy's nefarious attack. Create github actions to protect repo. | 3 | Create security on github | F:T | 1 | 1 | Matthew - 0%, Makai - 0%, Tyler - 50%, George - 50%, Camron - 0%
30 | Video Overview | Create a video to overview progress to the website | 3 | Create the entire video | NF:KA | 1 |  | Matthew - _%, Makai - _%, Tyler - _%, George - _%, Camron - _%
31 | Domain Model | Create the domain model, including links and other things | 3 | Complete the domain model paper | NF:KA | 2 |  | Matthew - _%, Makai - _%, Tyler - _%, George - _%, Camron - _%
32 | Switch the game dev environment to JS from Pygame | Change the framework from pygame to JS. Remove Pygame. Add JS. | 3 | Uninstall Pygame and install JS framework | F:T | 3 |  | Matthew - _%, Makai - _%, Tyler - _%, George - _%, Camron - _%

## Column Description
o Sprint Goal and Number. o Story copied from the project backlog or a sprint task story. o Story Type: F (functional), NF (non-functional) with a subtype: B (bug), T (technical work), KA(knowledge acquisition, technical or design/users). o Story Points. o Story Points Completed. o Team Member Names and percentage of contribution to the story.
Note there is another option this year to export this document instead from Github projects, see https://discord.com/channels/1280324227790278737/1280324228255711263/1291882302460399657